## Sheet1
Task Name | Estimate | Start Date | Task Owner | Assumptions / Known Issues / Notes
Project Problem Statement | 1 days | 2017-11-02 | Weston Nudell
Project Plan | 1 days | 2017-11-02 | Weston Nudell
Get Project Approved | 3 days | 2017-11-05 | Weston Nudell
Interview Potential Users | 1 days | 2017-11-08 | Computing Faculty
Document Requirements | 1 days | 2017-11-09 | Weston Nudell
Finalize Requirements | 1 days | 2017-11-10 | Weston Nudell
Design Classes | 1 days | 2017-11-11 | Weston Nudell
Document Technical Design | 1 days | 2017-11-12 | Weston Nudell | Include version control system, language, IDE, etc.
Design User Interface | 1 days | 2017-11-13 | Weston Nudell
Create Code Classes | 2 days | 2017-11-14 | Weston Nudell
Create User Interface | 2 days | 2017-11-16 | Weston Nudell
Write code for features | 3 days | 2017-11-18 | Weston Nudell
Connect Code Classes to UI | 1 days | 2017-11-21 | Weston Nudell
Wrtie Test Cases | 1 days | 2017-11-22 | Weston Nudell
Finalzie Code | 1 days | 2017-11-23 | Weston Nudell
Code Review | 1 days | 2017-11-24 | Weston Nudell
Test Code - Development | 1 days | 2017-11-25 | Weston Nudell
Deploy Program | 1 days | 2017-11-26 | Weston Nudell | Acquire Test Data
Test Deployment | 1 days | 2017-11-27 | Weston Nudell
Fix Issues | 3 days | 2017-11-28 | Weston Nudell
Submit Program | 0 days | 2017-12-02 | Weston Nudell